## Phase-1
Tasks | Expected Data of Completion
Setup Environment, GitHub, FastAPI installation, testing the POST method created in FastAPI using POSTMAN-(Ensuring seamless working of Backend) | 1
Validation of the POST method, importing the animateDiff model, testing with random prompts and images | 1 to 2
Engineering the best prompt for the application and merg with the additional information from the user. | 1
Integrating the theme, prompts and additional infos into the model, and testing if the model generating videos accurately. If yes, moves to next phase else optmization procedures will be done | 1
Total Days | 5